## Project Gantt Chart and Daily B
Main Task | Sub Task | Contributor | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
A. Case Study | Problem Statement | Atique |  |  | X
| SMART Objectives | Atique |  |  | X
| Target Users & Constraints | Atique |  |  | X
| GitHub Setup & Repo Management | Arafat |  |  | X | X | X | X
B/C. Design | IPO Analysis & Justification | Atique |  |  | X
| Algorithms & Pseudocode | Arafat |  |  |  | X
| Flowcharts (draw.io) | Arafat |  |  | X | X
D. Coding | Equipment Records & Data Structure | Arafat |  |  |  |  | X
| Input Validation & Update Logic | Arafat |  |  |  |  | X
| Energy/Cost Calcs & Surcharge | Arafat |  |  |  |  | X
| Alerts & Status Logic | Arafat | [5 empty] | X
| Bonus: File Handling (Optional) | Arafat |  |  |  | X | X | X
E/F. Testing | User Testing (30 Testers) | Arafat, Atique | [5 empty] | X
| Bug Fixes & Consistency Check | Arafat | [5 empty] | X
| Reflection & Personal Contribution | Arafat, Atique |  |  |  |  | X | X
Submission | Final Report Compilation (PDF) | Arafat, Atique |  |  |  |  | X | X